## RoC
RECORDS OF CHANGES
# | Date | In Charge | Change Notes
1
2
3
4
5
6
7

## Product
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Actual
1 | Update COVID test results |  | Simple | Nurse input COVID test result and system will notify the patient | Iteration
2 | View medical report | Public | Simple | Comprehensive report that covers a person’s clinical history. A medical report is a vital piece of evidence that can validate and support your claim for Social Security Disability benefits | Iteration
3 | View COVID test result | Public | Simple | Information you are positive or negative with covid-19 | Iteration
4 | Post List | Public | Simple | A list post is an article in a list format. It lists a number of reasons, tips, methods, | Iteration
5 | Post Detail | Public | Simple | Information of a post | Iteration
6 | Home Page | Common | Medium | Display slider, attractive posts, posts about clinic services, posts about medical information. - Information slider: image, title; users are redirected to the slider's backlink when they click. - Article information: thumbnail, title, category; users are redirected to Blog Details page when they click. - Service information: thumbnail, title, list price; users are redirected to service detail page when they click | Iteration 1
7 | User Login | Common | Simple | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Iteration 1
8 | User Register | Common | Simple | This is a pop-up screen which allows the user to register to the system by inputing following information: full name, DOB, gender, email, mobile, address,... | Iteration 1
9 | User Profile | Common | Simple | This is a pop-up screen which allows the user to edit his/her profile information, including the registered user information and the avatar image (s/he is not allowed to change the email) | Iteration 1
10 | Change Password | Common | Simple | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | Iteration 1
11 | Logout | Common | Simple |  | Iteration 2
12 | Book an appointment (test Covid) | Public | Medium | This screen allows the user to book an appointment for a covid test - user select covid test then | Iteration 2
13 | Book an appointment (examination) | Public | Simple | This screen allows the user to book an appointment for an medical examination - user select medical examination | Iteration 2
14 | Search patients |  | Simple | There will be a search box in patient list, user can search by name/phone number and the system will return patient list that conttain the typed word | Iteration 2
15 | Update medical report |  | Simple | Doctor can go to paitent's medical record and fill in it | Iteration 2
16 | Reset Password | Common | Medium | The user to input his/her email to receive the reset password link On clicking the link, the user is redirected to the page in which s/he input new password (twice) | Iteration 4
17 | User Authorization | Common | Complex | This is authorization mechanism in the system, including the specify the user's role, his/her authorized page links (building the displayed menu items and preventing unauthorized access via enter the links directly). The scope of this function also includes building the header, footer, the main function menu. | Iteration 4
18 | Appointment List |  | Simple | List of appointment include appointment medical examination and covid test
19 | Users List |  | Simple | List of user include patient, doctor,nurse
20 | Appointment Detail |  | Simple | detail infomation of an appointment
21 | Users Detail |  | Simple | detail infomation of a user

## Iteration 1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 1 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login |  | Simple |  | Trọng Tuấn | Done
2 | User Register |  | Medium |  | Hải Ninh | Done
3 | View User Profile |  | Medium |  | Hải Ninh | Done
4 | Logout |  | Simple |  | Trọng Tuấn | Done
5 | Update Profile |  | Medium |  | Hải Ninh | Done
6 | Change Passwword |  | Medium |  | Trọng Tuấn | Done
7

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 2 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Book an appointment (test Covid & health care) |  | Medium |  | Vinh | Done
2 | View appointment list |  | Simple |  | Vinh | Done
3 | Update appointment |  | Medium |  | Sơn | Done
4 | Delete appointment |  | Simple |  | Sơn | Done
5 | View detail appointment |  | Medium |  | Tuấn | Done
6 | Add medical record (health care) |  | Medium |  | Hoàng | Done
7 | Add medical record (test covid) |  | Medium |  | Tuấn | Done

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 3 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Create Health news |  | Complex |  | Hoàng | Done
2 | Update Health news |  | Medium |  | Hoàng | Done
3 | Delete Health news |  | Medium |  | Hoàng | Done
4 | Detail Health news |  | Medium |  | Hoàng | Done
5 | List Health news (admin) |  | Medium |  | Ninh | Done
6 | List Health news (home) |  | Complex |  | Ninh | Done
7 | List all user |  | Medium |  | Ninh | Done
8 | Filter user |  | Medium |  | Ninh | Done
9 | List all appointment |  | Medium |  | Vinh | Done
10 | Change appointment status |  | Medium |  | Vinh | Done
11 | Filter appointment |  | Medium |  | Sơn | Done
12 | Search appointment |  | Complex |  | Sơn | Done
13 | View result appointment (Test Covid) |  | Medium |  | Tuấn | Done
14 | View result appointment (health care) |  | Medium |  | Tuấn | Done
15